## Summary
Open-source publishing preparation
Executed publishing-prep plan for CanDoItAll.CodeAnalytics. Implementation, packaging docs, and proof artifacts are captured in the bundle.
Prepared bundle | CanDoItAll.CodeAnalsis.PublishPrepBundle | Status | Count | Formula | Notes
Current state | Execution complete through SB08 documentation updates; final validation proof captured in bundle proof folders. | Not Started |  |  | Final execution status
Highest blocker | No release-blocking validation blocker remains; segmented release matrix is the supported test strategy. | In Progress |  |  | File-length guardrail passes with warnings only
UI scope | Desktop large screen only; small and medium tuning intentionally out of scope. | Blocked |  |  | Browser proof captured at 1600x1000
EF conclusion | Static EF analyzer scope documented and tested; no runtime EF query tuning claims. | Complete |  |  | Runtime EF query tuning remains future scope
Critical subbundles | 5
Total subbundles | 8
Workbook generated | 2026-06-30 13:20
Checklist total

## Subbundle Plan
Subbundle plan
Execution order, dependencies, and gates for the publishing-preparation initiative.
ID | Name | Validation Depth | Prerequisites | Primary Deliverable | Status | Risk
SB01 | Validation Baseline And Release Guardrails | Critical foundation | None | Build/test/script baseline and XLSX artifact | Complete | Highest
SB02 | Architecture Seams And Project Extraction | Critical foundation | SB01 | Decide project/helper/driver/addon boundaries | Complete | High
SB03 | Application Service And Focused Context Refactor | Critical foundation | SB02 | Split app service, focused context, symbol query responsibilities | Complete | High
SB04 | Facts Collectors And EF Analyzer Hardening | Critical foundation | SB02 | Harden facts and EF analyzer capability | Complete | High
SB05 | Storage Rendering Export And Performance Hardening | Performance hardening | SB03, SB04 | Measure and harden storage/render/export/query hot paths | Complete | Medium
SB06 | Desktop Sandbox UI Decomposition | Desktop UI proof | SB03 | Split large Razor pages and prove large-screen workflows | Complete | Medium
SB07 | Open Source Packaging And Publishing Readiness | Publishing process | SB05, SB06 | Add OSS metadata, packability, package validation | Complete | Medium
SB08 | Documentation Overhaul And Final Closure Audit | Critical closure | SB07 | Docs updated, raw inputs closed, final validation proof captured | Complete | Highest

## Checklist
Detailed checklist
Editable execution checklist. Status and priority columns use validation lists.
ID | Subbundle | Task | Priority | Status | Acceptance Signal | Owner
CHK-001 | SB01 | Reproduce test hang and capture transcript | P0 | Complete | Test command returns or segmented matrix is documented | Execution agent
CHK-002 | SB01 | Fix or document file-length shell compatibility | P0 | Complete | Validate-FileLengths runs in documented shell | Execution agent
CHK-003 | SB01 | Finalize validation command matrix | P0 | Complete | Build, tests, scripts, validators have transcripts | Execution agent
CHK-004 | SB01 | Keep XLSX checklist current | P2 | Complete | Workbook generated during preparation | Preparation
CHK-005 | SB02 | Decide FocusedContext extraction | P0 | Complete | ADR states project or internal-service decision | Architecture
CHK-006 | SB02 | Decide EF analyzer addon boundary | P0 | Complete | Core/addon package decision is tested | Architecture
CHK-007 | SB02 | Protect allowed project references | P1 | Complete | Architecture tests guard reference direction | Architecture
CHK-008 | SB03 | Split focused-context strategy and scoring | P0 | Complete | Oversized strategy file reduced or justified | Application
CHK-009 | SB03 | Split symbol query/reference shaping | P0 | Complete | Symbols partial no longer owns all query behavior | Application
CHK-010 | SB03 | Add semantic focused-context tests | P0 | Complete | Positive and adversarial tests pass | Application
CHK-011 | SB04 | Harden DbContext/entity/relationship fixtures | P0 | Complete | EF analyzer tests cover expected facts | Facts
CHK-012 | SB04 | Avoid false runtime EF query claims | P0 | Complete | Negative tests prevent unsupported claims | Facts
CHK-013 | SB05 | Measure selected hot paths before optimizing | P1 | Complete | Scenario or benchmark baseline exists | Performance
CHK-014 | SB05 | Address dynamic regex safety | P1 | Complete | Timeout/cache/non-compiled decision is proven | Performance
CHK-015 | SB05 | Bound source/document reads | P2 | Complete | Large-file behavior is explicit and tested | Performance
CHK-016 | SB06 | Extract ContextLab components | P1 | Complete | Page no longer exceeds guardrail or has exception | Web
CHK-017 | SB06 | Extract snapshot context and symbol components | P1 | Complete | Large pages split into named components | Web
CHK-018 | SB06 | Capture desktop-large browser proof | P0 | Complete | Screenshots and visual review are recorded | Web
CHK-019 | SB07 | Add OSS license/security/contributing files | P0 | Complete | Repository hygiene files exist | Publishing
CHK-020 | SB07 | Add package metadata and packability matrix | P0 | Complete | dotnet pack and package inspection pass | Publishing
CHK-021 | SB08 | Rewrite README from shipped shape | P0 | Complete | Commands and claims are verified | Docs
CHK-022 | SB08 | Add ADRs for boundary decisions | P1 | Complete | Architecture decisions are durable | Docs
CHK-023 | SB08 | Close every raw input with proof | P0 | Complete | Raw note closure table has no pending rows | Closure

## Hotspots
Messy-part hotspot inventory
Files over thresholds, mixed responsibilities, and owning subbundles.
Lines | Path | Finding | Owner | Planned Handling
801 | tools/ScenarioEvaluationHarness/Program.cs | Tool monolith | SB07 | Documented as non-shipping harness for this wave; not packaged.
674 | tests/CanDoItAll.CodeAnalytics.Tests.Unit/ApplicationFacts.cs | Test monolith | SB01/SB03 | Split into ApplicationFacts, ApplicationFocusedContextFacts, and ApplicationSymbolFacts.
640 | src/CanDoItAll.CodeAnalytics.Application/Services/CodeAnalyticsApplicationService.Context.Strategy.cs | Focused-context strategy monolith | SB03 | Split strategy usage/models out of original partial; remaining warning below hard limit.
626 | tools/ComparisonHarness/Program.cs | Tool monolith | SB07 | Documented as non-shipping harness for this wave; not packaged.
619 | src/CanDoItAll.CodeAnalytics.Web/Components/Pages/ContextLab.razor | Razor page mixes UI/orchestration/helpers | SB06 | Extracted selected-files, usage-summary, and details panels; page below hard limit.
586 | src/CanDoItAll.CodeAnalytics.Application/Services/CodeAnalyticsApplicationService.Symbols.cs | Symbol query monolith | SB03 | Split context, models, search, and references partials.
414 | src/CanDoItAll.CodeAnalytics.Web/Components/Pages/Snapshots/Context.razor | Review-threshold UI page | SB06 | Reused shared focused-context components; page below review threshold.
368 | src/CanDoItAll.CodeAnalytics.Application/Services/CodeAnalyticsApplicationService.Context.SeedResolution.cs | Seed scoring mixed with service partial | SB03 | Warning-level file remains below hard limit; candidate for future resolver split.
358 | src/CanDoItAll.CodeAnalytics.Web/Components/Pages/Snapshots/Symbols.razor | Review-threshold UI page | SB06 | Warning-level page remains below hard limit; documented as future component split candidate.

## Extraction Candidates
Project and addon extraction candidates
Candidates to decide before code movement. These are decisions, not automatic moves.
Candidate | Current Source | Strength | Purpose | Decision Phase
FocusedContext | Application Context*.cs | Strong | Focused context seed/strategy/scoring/excerpts | Internal Application services now; separate project deferred.
SymbolQueries | Application Symbols*.cs | Medium | Symbol search, definitions, implementations, references | Internal Application partials now; separate project deferred.
Facts.EfCore | Facts/Persistence | Strong | Optional EF-specific analyzer addon over engine | Kept in Facts as static analyzer; future addon after fact-pack registration.
Facts.DependencyInjection | Facts/Services | Medium | Optional DI facts addon if package split is useful | Kept in Facts for this wave.
Storage.FileSystem | Storage | Medium | Filesystem snapshot storage driver | Kept as Storage driver project until a second driver exists.
Rendering.Mermaid | Rendering | Medium | Renderer package for Markdown/Mermaid exports | Kept in Rendering for this wave.
Web.DesktopSandbox | Web | Strong | Non-core desktop sandbox app | Non-packable desktop sandbox app.
Mcp.CodeAnalytics | reference/* | Future only | Thin future host driver, not this prep implementation | Future host driver only; not implemented here.

## Performance EF Scan
Performance and EF scan
Static scan results from preparation. Treat as triage until measured.
Recipe or Finding | Hit Lines | Triage | Owner
async-await-task | 187 | Async-heavy app; no issue by itself | SB01/SB05
sync-over-async | 4 | False positives on Result property names; no blocking sync-over-async found | SB01
indexof-literal | 0 | No literal overload issue found | None
substring | 0 | No hit | None
starts-ends-contains | 128 | Mixed collection and string calls; targeted review only | SB05
replace | 19 | Mostly path normalization, slug cleanup, Mermaid escaping | SB05
linq-select-where-order-group | 453 | Review only measured hot paths | SB03/SB05
new-dictionary-list | 68 | Expected in collectors/query paths; review repeated hot paths | SB03/SB05
regex-compiled | 2 | Dynamic RegexOptions.Compiled removed; generated regex remains valid. | SB05 complete
new-regex | 1 | Dynamic regex now timeout-bounded and fail-closed. | SB05 complete
file-io | 12 | Public source reads and export writes are bounded/contained. | SB05 complete
EF production runtime queries | 0 | No production runtime EF queries; static analyzer scope documented. | SB04 complete
EF fixture runtime queries | 2 | Fixture coverage supports static analyzer facts, not runtime query tuning claims. | SB04 complete

## Documentation Plan
Documentation improvement plan
Docs must be updated from shipped implementation decisions, not from preparation guesses.
Artifact | Current State | Needed Improvement | Dependency | Owner
README | Publishing-ready overview | Public API, validation, sandbox, and packaging docs complete | SB08 complete | SB08
ADRs | Accepted ADR set | Boundary, EF/performance, packaging, sandbox, and driver decisions complete | SB08 complete | SB08
License | MIT license present | Package license metadata present | SB07 complete | SB07
Security | SECURITY.md present | Vulnerability process documented | SB07 complete | SB07
Contributing | CONTRIBUTING.md present | Contribution and validation workflow documented | SB08 complete | SB08
Reference docs | Updated reference set | Public API, desktop sandbox, publishing, EF, performance, and driver docs aligned | SB08 complete | SB08
Harness docs | Non-shipping tool posture documented | No harness package shipped | SB07/SB08 complete | SB08